## Sprint 1
| Day 0 | 2020-03-25 | 2020-04-01 | 2020-04-15 | Task | Estimated time (in hours) | Actual time (in hours) | Day 1 | Day 2 | Day 3 | Student
Expected remaining hours | 155 | 103.3333 | 51.6667 | 0 | Android
Actual remaining hours | 176 | 114.3333 | 50.1667 | -2 | Create the architecture of the system and prepare all the packages for the implementations | 3 | 4 | 2 | 2 |  | Valeriu Rusu, Valeriu Marandici, David
[5 empty] | Create the MainActivity with a tablayout for implementation | 2 | 2 | 1 | 1 |  | Valeriu Rusu
[5 empty] | Create the layout of the MainActivity | 2 | 2 | 2 |  |  | Valeriu Rusu
[5 empty] | Create MuseumFragment | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create ArtworksTabFragment | 1 | 1 | 1 |  |  | Valeriu Rusu, David
[5 empty] | Create RoomsTabFragment | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Create ArtworksTabViewModel | 1 | 1 | 1 |  |  | David
[5 empty] | Create RoomsTabViewModel | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Create MuseumTabViewModel | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Create ArtoworksRepository | 2 | 3 |  | 1 | 2 | Valeriu Rusu
[5 empty] | Create AddArtworkView | 2 | 3 | 1 | 1 | 1 | David
[5 empty] | Create AddArtworkViewModel | 1 | 1 |  | 1 |  | David
[5 empty] | Create EditArtworkView | 3 | 2 |  | 2 |  | David
[5 empty] | Create EditArtworkViewModel | 1 | 1 |  |  | 1 | David
[5 empty] | Create the adapter for the RecyclerView in ArtworksTab | 3 | 3 |  | 1 | 2 | David, Valeriu Rusu
[5 empty] | Create the Model | 2 | 2 |  | 2 |  | David
[5 empty] | Prepare the ServiceGenerator for artworks calls | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Prepare the calls with retrofit to get all artworks | 1 | 2 |  |  | 2 | Valeriu Rusu
[5 empty] | Prepare the calls with retrofit to add an artwork | 1 | 2 |  |  | 2 | Valeriu Rusu
[5 empty] | Prepare the calls with retrofit to edit an artwork | 1 | 1 |  |  | 1 | Valeriu Rusu
[5 empty] | Prepare the call with retrofit to delete an artwork | 1 | 1 |  |  | 1 | Valeriu Rusu
[5 empty] | Prepare the storage room | 2 | 2 |  | 2 |  | Valeriu Marandici
Data Warehouse
[5 empty] | Create the architecture of the system and prepare all the packages for the implementations (including rest API) | 10 | 14 | 7 | 3 | 4 | Florin
[5 empty] | Create arquitecture diagram | 2 | 2 | 2 | 2 |  | Jaume
[5 empty] | Create class diagram for the system | 7 | 7 | 3 | 4 |  | Jaume | Sabin
[5 empty] | Create ER diagram for source database | 2 | 2 |  |  | 2 | Jaume
[5 empty] | Create Artwork Repository | 4 | 5 | 1 | 2 | 2 | Florin
[5 empty] | Create source database | 6 | 8 | 3 | 3 | 2 | Florin
[5 empty] | Create viewArtworks conservation details endpoint | 2 | 2 |  |  | 2 | Florin
[5 empty] | Create repository base class and interface | 3 | 4 |  | 1 | 3 | Florin
[5 empty] | Create manage artworks endpoints | 4 | 4 |  | 2 | 2 | Florin
[5 empty] | Create datamodel | 2 | 2 | 1 | 0.5 | 0.5 | Florin
IOT
[5 empty] | Create estimates and list all the tasks | 1 | 1 | 1 |  |  | Fabian
[5 empty] | Refactor Analysis | 8 | 10 | 4 | 5 | 1 | Marina, Fabian
[5 empty] | Create IoT branch | 1 | 1 | 1 |  |  | Marina
[5 empty] | Research Via Iot Driver guides | 3 | 4 | 2 | 1 | 1 | Marina, Fabian, Dementie, Justinas
Analysis and Common Tasks
[5 empty] | Git repository | 1 | 1 | 1 |  |  | Jaume
[5 empty] | View artworks convervation details - use case description, activity diagram, test cases, system sequence diagram | 3 | 4 | 2 | 2 |  | Valeriu Marandici, Fabian
[5 empty] | Manage user's accounts/Manage my account- use case description, activity diagram, test cases, system sequence diagram | 3 | 3 | 3 |  |  | Dementie, Sabin
[5 empty] | Manage rooms - use case description, activity diagram, test cases, system sequence diagram | 3 | 3 |  | 3 |  | Marina
[5 empty] | Manage artworks - use case description, activity diagram, test cases, system sequence diagram | 3 | 4 | 2 | 2 |  | Valeriu Marandici, Fabian
[5 empty] | View artworks - use case description, activity diagram, test cases, system sequence diagram | 3 | 2 | 1 | 1 |  | Valeriu Marandici, Fabian
[5 empty] | Add artwork - use case description, activity diagram, test cases, system sequence diagram | 3 | 3 |  | 2 | 1 | Valeriu Marandici, Fabian
[5 empty] | Delete artwork - use case description, activity diagram, test cases, system sequence diagram | 3 | 3 |  |  | 3 | Valeriu Marandici, Fabian
[5 empty] | Design domain model | 2 | 3 | 2 | 1 |  | Marina, Fabian
[5 empty] | Log in system analysis | 2 | 3 |  |  | 3 | Valeriu Rusu
[5 empty] | Create system architecture diagram | 3 | 4 | 2 | 2 |  | Marina
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 155 | 176 | 61.6667 | 64.1667 | 52.1667

## Sprint 2
| Day 0 | 2020-04-29 | 2020-05-06 | 2020-05-13 | Task | Estimated time (in hours) | Actual time (in hours) | Day 1 | Day 2 | Day 3 | Student
Expected remaining hours | 150 | 100 | 50 | 0 | Android
Actual remaining hours | 180 | 114.3333 | 42.6667 | -8 | Prepare the Local Storage (Room Database) for the local data | 5 | 8 | 6 | 2 |  | David
[5 empty] | Create EditRoomActivity view (the view responsible for setting the optimal conditions and edit them) | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Create EditRoomActivityViewModel | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Connect the view model with the repository | 1 | 1 | 1 |  |  | David
[5 empty] | Prepare the Endpoints | 2 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create the MuseumTab View | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create the MuseumTavViewModel | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create The Rooms Views (we have 7 rooms in the Museum) | 7 | 6 | 5 | 1 |  | Valeriu Rusu
[5 empty] | Create the Rooms View Models | 2 | 3 |  | 3 |  | Valeriu Rusu
[5 empty] | Prepare the api the request for getting the artworks from the specific room with the endpoint by the roomCode "/artworks?roomCode={roomCode}" | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Create the layout for the MuseumTab (with the image of a museum plan) | 3 | 3 |  | 3 |  | Valeriu Rusu
[5 empty] | Create the layout for each room in the Museum (7 rooms - 7 layouts) | 7 | 9 |  | 5 | 4 | Valeriu Rusu
[5 empty] | Create an Artwork Details View ( the view for the pop up when you click on an artwork in the room) | 2 | 2 |  |  | 2 | Valeriu Rusu
[5 empty] | Create the Artwork Details View Model | 2 | 1 |  |  | 1 | Valeriu Rusu
[5 empty] | Create RoomArtworksActivity (the view which will display all the artworks in the specific room in the Rooms Tab) | 3 | 4 | 4 |  |  | Valeriu Marandici
[5 empty] | Create an adapter for the artworks in a specific room | 3 | 3 | 3 |  |  | Valeriu Marandici
[5 empty] | Create Room Conditions View | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Create Room View | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Create Room View Model | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Create Room Repository | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Create Room Conditions View Model | 1 | 1 |  |  | 1 | Valeriu Marandici
[5 empty] | Create the adapter for the rooms | 1 | 2 |  | 1 | 1 | Valeriu Marandici
[5 empty] | Create the adapter for the specific room with the artworks | 3 | 3 |  |  | 3 | Valeriu Marandici
[5 empty] | Create the Theme of the system | 4 | 4 |  |  | 4 | David
Data Warehouse
[5 empty] | Prepare the endpoint for the put request from the postman where we edit the environmental conditions | 1 | 3 | 1 | 1 | 1 | Florin,Sabin
[5 empty] | getMeasurements() method which will return the measurements in a room | 3 | 5 | 2 | 2 | 1 | Jaume
[5 empty] | Transform data from IoT | 5 | 3 | 4 | 4 |  | Jaume
[5 empty] | getRoomsDetails() which will return all the parameters from the Room Model | 2 | 4 | 2 |  | 2 | Florin
[5 empty] | Connect to the MongoDB database | 3 | 2 | 2 |  |  | Jaume
[5 empty] | Create Measurements repository | 3 | 2 | 3 | 1 | 1 | Jaume
[5 empty] | Create Room repository | 1 | 3 | 1 | 1 | 1 | Sabin, Florin
[5 empty] | Update the endpoints by the template in the Postman | 1 | 1 |  | 1 |  | Florin
[5 empty] | Redo Room Repository | 2 | 4 | 1 | 2 | 1 | Florin
[5 empty] | Implement view artwork placement | 1 | 2 |  | 1 | 1 | Florin
IOT
[5 empty] | Create estimates and list all the tasks | 1 | 1 | 1 |  |  | Fabian
[5 empty] | Take the hardware | 1 | 1 | 1 |  |  | Fabian, Justinas
[5 empty] | Refactor Analysis | 13 | 25 | 7 | 13 | 5 | Marina, Fabian
[5 empty] | Research Via Iot Driver guides | 2 | 5 |  | 3 | 2 | Marina, Fabian, Justinas, Dementie
[5 empty] | Design main model of the embedded system | 5 | 4 |  | 2 | 2 | Marina, Fabian, Justinas
[5 empty] | Create MongoDb database for the project | 3 | 3 | 3 |  |  | Marina
[5 empty] | Generate json schema for the records placed in the MongoDb database | 1 | 1 | 1 |  |  | Marina
[5 empty] | Generate random testing data for the Data Engineering Team | 1 | 1 |  |  | 1 | Marina
[5 empty] | Design Bridge app | 2 | 4 |  | 4 |  | Marina
[5 empty] | Implement Bridge app | 5 | 5 |  | 2 | 3 | Marina
[5 empty] | Refactor domain model | 2 | 2 |  | 2 |  | Marina, Fabian
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 150 | 180 | 65.6667 | 71.6667 | 50.6667

## Sprint 3
| Day 0 | 2020-05-20 | 2020-05-21 | 2020-05-22 | Task | Estimated time (in hours) | Actual time (in hours) | Day 1 | Day 2 | Day 3 | Student
Expected remaining hours | 145 | 96.6667 | 48.3333 | 0 | Android
Actual remaining hours | 161 | 107.3333 | 45.6667 | -3 | Update the Artworks Adapter in order to filter the artworks | 2 | 1 | 1 |  |  | David
[5 empty] | Add Search toolbar | 1 | 1 | 1 |  |  | David
[5 empty] | Implement the menuOptions in the view | 1 | 1 | 1 |  |  | David
[5 empty] | Update the model of the Artwork | 0.5 | 0.5 | 0.5 |  |  | David
[5 empty] | Update the view with the comments | 1 | 1 |  | 1 |  | David
[5 empty] | Update the data that we are sending in the requests in the repository | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create Administrator Model | 1 | 0.5 | 0.5 |  |  | Valeriu Marandici
[5 empty] | Create the Admin View | 2 | 2 |  | 2 |  | David, Valeriu Rusu
[5 empty] | Update the request with the required method for the admin | 1 | 2 | 2 |  |  | Valeriu Rusu
[5 empty] | Create Admin View Model | 1 | 1 | 1 |  |  | David
[5 empty] | Update the endpoint to move the artwork | 1 | 1 |  |  | 1 | Valeriu Rusu
[5 empty] | Create a new button to move the artwork | 1 | 1 |  |  | 1 | Valeriu Rusu
Data Warehouse
[5 empty] | Create registerUser endpoint | 2 | 3 | 3 |  |  | Jaume
[5 empty] | Update model of the artwork | 0.5 | 1 | 1 |  |  | Florin
[5 empty] | Implement search artwork endpoint | 1 | 2 | 1 | 1 |  | Florin
[5 empty] | Move database to cloud deployment/ remote server | 4 | 7 | 1 | 2 | 4 | Florin
[5 empty] | Update and edit room repository and controller | 2 | 3 |  | 1 | 2 | Florin
[5 empty] | Create account repository | 4 | 4 | 4 |  |  | Jaume
[5 empty] | Create updateUser endpoint | 3 | 3 | 1 | 1 | 1 | Jaume
[5 empty] | Create deleteUser endpoint | 3 | 3 | 1 | 1 | 1 |  | Jaume
[5 empty] | Create ETL excel sheets | 11 | 11 | 3 | 4 | 4 | Florin | Jaume | Sabin
[5 empty] | Create activity diagrams for creating dimensions | 4 | 4 | 1 | 2 | 1 | Florin | Jaume | Sabin
[5 empty] | Create busines needs for datawarehouse | 11 | 11 | 5 | 4 | 2 | Florin | Jaume | Sabin
IOT
[5 empty] | Create estimates and list all the tasks | 2 | 2 | 1 | 1 |  | Fabian
[5 empty] | Research Via Iot Driver guides | 5 | 5 | 2 | 2 | 1 | Marina, Fabian, Justinas, Dementie
[5 empty] | Create design class diagram | 5 | 6 | 3 | 3 |  | Marina, Fabian
[5 empty] | Create sequence diagram sensorControl_create | 2 | 2 |  | 2 |  | Marina
[5 empty] | Create IoT Sequence diagram for the continuous call | 3 | 3 |  | 3 |  | Fabian
[5 empty] | Setup drivers | 2 | 1 | 1 |  |  | Marina
[5 empty] | Implement sensor data package handler | 3 | 3 | 3 |  | 3 | Marina
[5 empty] | Implemement Lorawan Task | 3 | 6 | 2 | 4 |  | Marina
[5 empty] | Implement Light sensor | 3 | 6 |  | 3 | 3 | Marina
[5 empty] | Implement sensor control | 5 | 5 |  | 5 |  | Marina
[5 empty] | Generate new data in test collection to include light values | 1 | 1 |  |  | 1 | Fabian
[5 empty] | Debug and prepare the system for the proof of concept | 5 | 7 |  | 1 | 6 | Marina
[5 empty] | Record the continuous call from the light sensor to the database | 2 | 2 |  | 2 |  | Marina
[5 empty] | Record audio for the proof of concept video | 1 | 1 |  |  | 1 | Fabian
[5 empty] | Edit proof of concept video | 1 | 1 |  |  | 1 | Justinas
[5 empty] | Write test cases for white box testing | 3 | 3 |  | 2 | 1 | Justinas
[5 empty] | Write black box test cases for the parts that cannot be unit tested | 3 | 3 |  | 2 | 1 | Justinas, Dementie
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 145 | 161 | 53.6667 | 61.6667 | 48.6667

## Sprint 4
| Day 0 | 2020-05-25 | 2020-05-26 | 2020-05-27 | Task | Estimated time (in hours) | Actual time (in hours) | Day 1 | Day 2 | Day 3 | Student
Expected remaining hours | 140 | 93.3333 | 46.6667 | 0 | Android
Actual remaining hours | 165 | 120.3333 | 63.6667 | 1 | Create the endpoint for edit | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update the artworks repository with the method for edit passing the edited artwork | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update the APIClient with the Call | 1 | 1 |  |  | 1 | Valeriu Rusu
[5 empty] | Restructure the ViewModel to extend AndroidViewModel | 2 | 1 | 1 |  |  | Valeriu Rusu, Valeriu Marandici, Dave
[5 empty] | Update location when artwork added | 3 | 3 | 1 | 2 |  | Dave
[5 empty] | Update the model of the Artwork | 1 | 1 |  | 1 |  | Valeriu Marandici
[5 empty] | Update the view with the comments | 2 | 2 |  | 2 |  | Valeriu Marandici
[5 empty] | Update the data that we are sending in the requests in the repository | 3 | 3 |  |  | 3 | Valeriu Rusu
[5 empty] | Create ArtworksDetailsTest (UI with Espresso) with the test of openning a specific room | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create ArtworksDetailsTest (UI with Espresso) with the test of choosing a specific artwork | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create ArtworksDetailsTest (UI with Espresso) with the test of returning to the main activity | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Create ArtworksTabTest (UI with Espresso) with the test of opening the ArtworksTab and displaying all the necessary information | 1 | 1 | 1 |  |  | Valeriu Rusu
Data Warehouse
[5 empty] | Create the endpoint for editArtwork | 3 | 3 | 1 | 2 |  | Florin
[5 empty] | Update the model of the Artwork with comments | 0.5 | 1 | 1 |  |  | Florin
[5 empty] | Create the moveArtwork endpoint | 5 | 5 | 2 |  | 3 | Florin
[5 empty] | Create datawarehouse and prepare database in azure cloud | 8 | 15 | 4 | 7 | 4 | Florin,Sabin,Jaume
[5 empty] | Create Star schemas | 3 | 3 | 1 |  | 2 | Florin | Sabin | Jaume
[5 empty] | Implement update artwork location when added to a new room | 3 | 5 | 2 | 2 | 1 | Florin
[5 empty] | Implement and test SQL queries to source database from rest api | 7 | 7 | 3 | 1 | 3 | Florin
[5 empty] | Create staging database and datawarehouse database tables | 12 | 12 | 4 | 5 | 3 | Jaume | Sabin | Florin
[5 empty] | Fix - Continue Move source database to the cloud | 8 | 11 | 3 | 2 | 5 | Florin
IOT
[5 empty] | Create estimates and list all the tasks | 2 | 2 | 2 |  |  | Fabian
[5 empty] | Update design class diagram to include temperature / humidity and co2 sensors | 2 | 2 |  | 2 |  | Marina, Fabian
[5 empty] | Implement co2 sensor | 5 | 7 |  | 7 |  | Fabian, Justinas
[5 empty] | Implement Temperature/humidity sensor | 3 | 5 |  |  | 5 | Fabian
[5 empty] | Create window shutters user story | 1 | 1 |  | 1 |  | Fabian
[5 empty] | Refactor design | 5 | 3 |  |  | 3 | Marina, Fabian
[5 empty] | Refactor test cases white / black box | 5 | 2 |  | 2 |  | Justinas, Dementie
[5 empty] | Debugging for sensors | 8 | 20 |  | 8 | 12 | Marina, Fabian, Justinas
[5 empty] | Generate additional data for more rooms | 1 | 1 |  |  | 1 | Marina
[5 empty] | Refactor code | 3 | 3 |  |  | 3 | Marina, Fabian
[5 empty] | Write Windows shutters use case | 1 | 1 | 1 |  |  | Fabian
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 140 | 165 | 44.6667 | 56.6667 | 62.6667

## Sprint 5
| Day 0 | 2020-05-28 | 2020-05-29 | 2020-06-01 | Task | Estimated time (in hours) | Actual time (in hours) |  |  |  | Student
Expected remaining hours | 131 | 87.3333 | 43.6667 | 0 | Android
Actual remaining hours | 155 | 102.3333 | 58.6667 | 0 | Create NotificationsRepository | 2 | 4 | 4 |  |  | Valeriu Marandici
[5 empty] | Create NotificationsEndpoints | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Create the calls in the repository | 2 | 1 | 1 |  |  | David
[5 empty] | Create the LoginActivity | 3 | 5 | 5 |  |  | Valeriu Rusu, David
[5 empty] | Create LoginViewModel | 1 | 1 | 1 |  |  | Valeriu Rusu, David
[5 empty] | Create the AuthRepository | 2 | 2 | 2 |  |  | Valeriu Rusu
[5 empty] | Create the AuthEndpoints | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update the endpoint for login | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Create the calls in the APIClient | 1 | 1 |  | 1 |  | Valeriu Rusu, David
[5 empty] | Create the toolbar for the account | 1 | 1 |  | 1 |  | David
[5 empty] | Create the account view | 2 | 2 |  |  | 2 | David
[5 empty] | Create the adapter for the account view | 2 | 2 |  |  | 2 | David
[5 empty] | Create the viewModel for AccountView | 1 | 1 |  |  | 2 | David
[5 empty] | Create the viewModel for DataVisualization | 1 | 1 | 1 |  |  | Valeriu Marandici
[5 empty] | Create the view for DataVisualization | 5 | 7 | 3 |  | 4 | Valeriu Marandici
[5 empty] | Create Setting view and view model | 4 | 4 | 2 | 2 |  | Valeriu Marandici, David
Data Warehouse
[5 empty] | Create the getUsers endpoint | 2 | 2 | 2 |  |  | Jaume
[5 empty] | Create the validateLogin endpoint | 2 | 2 |  | 2 |  | Jaume
[5 empty] | Create the endpoint for the notifications | 4 | 5 |  | 5 |  | Jaume
[5 empty] | Create Visitor repository | 1 | 1 | 1 |  |  | Florin
[5 empty] | Attempt linked databases servers to perform cross database queries | 3 | 5 | 1 | 1 | 3 | Florin
[5 empty] | Implement different way to transfer data from mongoDB to SQLServer | 3 | 3 | 1 | 1 | 1 | Florin
[5 empty] | Update and fix database from previous changes that have been done without migrations, fix migration files and re-do migrations | 2 | 3 | 1 |  | 2 | Florin
[5 empty] | ETL procceses | 8 | 10 | 3 | 4 | 3 | Jaume | Sabin | Florin
IOT
[5 empty] | Create estimates and list all the tasks | 2 | 2 | 2 |  |  | Fabian
[5 empty] | Design RcServoHandler | 1 | 2 |  | 2 |  | Marina
[5 empty] | Implement RcServoHandler | 1 | 2 |  | 2 |  | Marina
[5 empty] | Debug RcServoHandler | 2 | 5 |  | 2 |  | Marina
[5 empty] | Update design class diagram to include RcServoHandler | 1 | 2 |  | 2 |  | Fabian
[5 empty] | Degugging | 5 | 6 |  | 2 | 4 | Marina, Fabian
[5 empty] | Refactor code | 2 | 2 |  |  | 2 | Fabian
[5 empty] | Write additional code comments | 2 | 2 | 1 |  | 1 | Fabian
[5 empty] | Write IoT app documentation | 5 | 2 |  |  | 2 | Justinas, Dementie
[5 empty] | Refactor Iot app documentation | 3 | 5 |  | 3 | 2 | Marina, Fabian
[5 empty] | Write documentation for the bridge app | 2 | 2 |  |  | 2 | Marina
[5 empty] | Create and setup test project for iot | 2 | 7 | 7 |  |  | Marina
[5 empty] | Add the functionality to save logs of bridge app to a file | 1 | 3 |  |  | 3 | Marina
[5 empty] | Refactor and check create sequence diagram | 2 | 2 |  |  | 2 | Marina
[5 empty] | Refactor and check system flow sequence diagram | 2 | 2 |  |  | 2 | Fabian
[5 empty] | Delete useless entries MongoDb | 1 | 1 |  |  | 1 | Fabian
[5 empty] | Refacor test cases | 5 | 3 |  |  | 3 | Marina, Fabian
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 131 | 155 | 52.6667 | 43.6667 | 56.6667

## Sprint 6
| Day 0 | 2020-06-02 | 2020-06-03 | 2020-06-04 | Task | Estimated time (in hours) | Actual time (in hours) | Day 1 | Day 2 | Day 3 | Student
Expected remaining hours | 303 | 202 | 101 | 0 | Android
Actual remaining hours | 324 | 218.3333 | 102.6667 | 1 | Update ArtworksDetailsTest (UI with Espresso) with the test of openning a specific room | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update ArtworksDetailsTest (UI with Espresso) with the test of choosing a specific artwork | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update ArtworksDetailsTest (UI with Espresso) with the test of returning to the main activity | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update ArtworksTabTest (UI with Espresso) with the test of opening the ArtworksTab and displaying all the necessary information | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update LoginActivityTest (UI with Espresso) with the test of inputing the email | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update LoginActivityTest (UI with Espresso) with the test of inputing the password | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update LoginActivityTest (UI with Espresso) with the test of logging in | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update ManageAccountsTest (UI with Espresso) with the test of openning the ManageAccountsActivity and displaying the relevant data | 1 | 1 | 1 |  |  | Valeriu Rusu
[5 empty] | Update the MuseumTabTest (UI with Espresso) with the test of openning the MuseumTab and displaying the relevant data | 1 | 2 | 1 | 1 |  | Valeriu Rusu
[5 empty] | Update a test for a opening a specific room in the museum (UI with Espresso) and displaying all the relevant data | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Update the RoomsTabTest (UI with Espresso) with the test of openning the RoomsTab and displaying the relevant data | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Update the StorageTabTest (UI with Espresso) with the test of openning the StorageTab and displaying the relevant data | 1 | 1 |  | 1 |  | Valeriu Rusu
[5 empty] | Update the ArtworksTabTest (Junit test) to check if the recycler view is clicked | 3 | 4 |  | 4 |  | David, Valeriu Marandici
[5 empty] | Update the RoomsTest (Junit test) for changeCelsiusToFahrenheit | 4 | 4 |  | 4 |  | David, Valeriu Marandici
[5 empty] | Update the validator test (Junit test) | 5 | 5 |  |  | 5 | David, Valeriu Marandici, Valeriu Rusu
[5 empty] | Project Report documentation | 34 | 38 | 12 | 9 | 17 | David, Valeriu Marandici, Valeriu Rusu
[5 empty] | Process Report documentation | 30 | 31 | 10 | 9 | 12 | David, Valeriu Marandici, Valeriu Rusu
Data Warehouse
[5 empty] | Test rest API | 5 | 8 | 3 | 3 | 2 | Florin
[5 empty] | Implement slowly changes | 9 | 9 | 4 | 5 |  | Sabin
[5 empty] | Incremental loading | 9 | 11 |  | 4 | 7 | Sabin | Jaume
[5 empty] | Test SQL | 2 | 4 | 4 |  |  | Sabin
[5 empty] | Project Report documentation | 28 | 34 | 12 | 15 | 7 | Florin,Jaume,Sabin
[5 empty] | Process Report documentation | 30 | 32 | 9 | 9 | 14 | Florin,Jaume,Sabin
IOT
[5 empty] | Create estimates and list all the tasks | 1 | 1 | 1 |  |  | Fabian
[5 empty] | Generate documentation using Doxygen | 1 | 1 | 1 |  |  | Marina
[5 empty] | Test bridge application | 2 | 1 | 1 |  |  | Marina
[5 empty] | Deploy Bridge App on Linux server | 1 | 1 |  | 1 |  | Marina
[5 empty] | Make RcServo a task in design diagrams | 1 | 2 | 2 |  |  | Fabian
[5 empty] | Make RcServo a task in implementation | 1 | 1 |  |  |  | Marina
[5 empty] | Make RcServo work | 1 | 3 | 1 | 2 |  | Marina
[5 empty] | Test sensor data package handler | 2 | 3 |  | 3 |  | Marina
[5 empty] | Run the application in different places at different time intervalsthe application | 1 | 1 | 1 |  |  | Marina
[5 empty] | Test application using black box | 2 | 2 | 1 | 1 |  | Marina
[5 empty] | Refactor the mistakes in estimates | 2 | 2 | 2 |  |  | Fabian
[5 empty] | Test co2 task using white box | 2 |  |  |  |  | Not done
[5 empty] | Test temperature/humidity task using white box | 2 |  |  |  |  | Not done
[5 empty] | Test light task using white box | 2 |  |  |  |  | Not done
[5 empty] | Test Rc Servo using white box | 2 |  |  |  |  | Not done
[5 empty] | Test sensor control using white box | 2 |  |  |  |  | Not done
[5 empty] | Test LoraWan task using white box | 2 |  |  |  |  | Not done
[5 empty] | Project Report documentation | 34 | 40 | 20 | 10 | 10 | Marina, Justinas, Dementie, Fabian
[5 empty] | Process Report documentation | 34 | 34 |  | 20 | 14 | Marina, Justinas, Dementie, Fabian
[5 empty] | Scrum documentation | 3 | 4 | 1 | 1 | 2
[5 empty] | Meetings | 34 | 35 | 11.6667 | 11.6667 | 11.6667
[5 empty] | Total | 303 | 324 | 105.6667 | 115.6667 | 101.6667

## FinalResult
Burndown Chart
[8 empty] | Sprints | Estimated time (in hours) | Actual time (in hours)
[8 empty] | Sprint 1 | 155 | 176
[8 empty] | Sprint 2 | 150 | 180
[8 empty] | Sprint 3 | 145 | 161
[8 empty] | Sprint 4 | 140 | 165
[8 empty] | Sprint 5 | 131 | 155
[8 empty] | Sprint 6 | 303 | 324
[8 empty] | Total | 1024 | 1161
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6
Ideal estimated time (in hours) | 1024 | 853.3333 | 682.6667 | 512 | 341.3333 | 170.6667 | 0
Actual estimated time (in hours) | 1024 | 869 | 719 | 574 | 434 | 303 | 0
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | IOT TRIAL
Estimated time (in hours) | 245 | 204.1667 | 163.3333 | 122.5 | 81.6667 | 40.8333 | 0 | Sprints | Estimated time (in hours) | Actual time (in hours)
Actual time (in hours) | 245 | 232 | 198 | 149 | 117 | 79 | 0 | Sprint 1 | 13 | 16
[8 empty] | Sprint 2 | 34 | 60
[8 empty] | Sprint 3 | 49 | 57
[8 empty] | Sprint 4 | 32 | 46
[8 empty] | Sprint 5 | 38 | 52
[8 empty] | Sprint 6 | 79 | 87
[8 empty] | Total | 245 | 318
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Android TRIAL
Estimated time (in hours) | 230.5 | 192.0833 | 153.6667 | 115.25 | 76.8333 | 38.4167 | 0 | Sprints | Estimated time (in hours) | Actual time (in hours)
Actual time (in hours) | 230.5 | 196.5 | 141.5 | 128 | 114 | 88 | 0 | Sprint 1 | 34 | 38
[8 empty] | Sprint 2 | 55 | 56
[8 empty] | Sprint 3 | 13.5 | 11
[8 empty] | Sprint 4 | 14 | 13
[8 empty] | Sprint 5 | 26 | 31
[8 empty] | Sprint 6 | 88 | 95
[8 empty] | Total | 230.5 | 244
| Sprint 0 | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | DATA WAREHOUSE TRIAL
Estimated time (in hours) | 266.5 | 222.0833 | 177.6667 | 133.25 | 88.8333 | 44.4167 | 0 | Sprints | Estimated time (in hours) | Actual time (in hours)
Actual time (in hours) | 266.5 | 224.5 | 202.5 | 157 | 108 | 83 | 0 | Sprint 1 | 42 | 50
[8 empty] | Sprint 2 | 22 | 29
[8 empty] | Sprint 3 | 45.5 | 52
[8 empty] | Sprint 4 | 49 | 62
[8 empty] | Sprint 5 | 25 | 31
[8 empty] | Sprint 6 | 83 | 98
[8 empty] | Total | 266.5 | 322